## excel
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Edgar Alexander Aguilar BolaÃ±os
Start Date | may 02, 2017 11:14:51 AM
Completion Date | may 03, 2017 03:04:42 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 30.4 | 30.5 | 31.2
Planned Time | 0.26319 |  | 1899-12-31 22:34
Actual Time |  | 0.31389 | 1900-01-01 02:58
CPI (Cost-Performance Index) |  |  | 0.91
% Reuse | 0% | 0% | 3.37%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 16.2 | 21.7 | 17
Total Defects/KLOC or equivalent | 33.8 | 43.5 | 35.2
Yield % | 52.2% | 50% | 51.8%
Code Review Rate | 1099 | 920 | 1097
% Appraisal COQ | 3.95% | 5.31% | 4.15%
% Failure COQ | 14% | 16.8% | 14.4%
COQ A/F Ratio | 0.28 | 0.32 | 0.29
PQI | 0.01 | 0.01 | 0.01
Program Size
| Plan | Actual | To Date
Base (B) | 725 | 725 | 1370
Deleted (D) | 0 | 0 | 2
Modified (M) | 0 | 0 | 6
Added (A) | 192 | 230 | 1585
Reused (R) | 0 | 0 | 97
Added and Modified (A+M) | 192 | 230 | 1591
Total Size (T) | 917 | 955 | 2880
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 189 | 230 | 1711
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | To Date | To Date %
Planning | 0.057639 | 0.0875 | 0.48403 | 22.8%
Design | 0.050694 | 0.036111 | 0.38611 | 18.2%
Design Review | 0.0034722 | 0.00625 | 0.027778 | 1.31%
Code | 0.08125 | 0.088889 | 0.64583 | 30.4%
Code Review | 0.0069444 | 0.010417 | 0.060417 | 2.84%
Compile | 0 | 0 | 0.0020833 | 0.1%
Test | 0.036111 | 0.052778 | 0.30347 | 14.3%
Postmortem | 0.026389 | 0.031944 | 0.21389 | 10.1%
Total | 0.26319 | 0.31389 | 1900-01-01 02:58
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | To Date | To Date %
Before Development | 0 | 0 | 0 | 0%
Planning | 0.28 | 0 | 2 | 3.57%
Design | 1.83 | 4 | 17 | 30.4%
Design Review | 0 | 0 | 0 | 0%
Code | 4.36 | 6 | 37 | 66.1%
Code Review | 0 | 0 | 0 | 0%
Compile | 0 | 0 | 0 | 0%
Test | 0 | 0 | 0 | 0%
Total | 6.47 | 10 | 56
Defects Removed
| Plan | Actual | To Date | To Date %
Planning | 0 | 0 | 0 | 0%
Design | 0.14 | 0 | 1 | 1.79%
Design Review | 0.14 | 2 | 3 | 5.36%
Code | 1.69 | 2 | 14 | 25%
Code Review | 1.41 | 1 | 11 | 19.6%
Compile | 0 | 0 | 0 | 0%
Test | 3.1 | 5 | 27 | 48.2%
Total | 6.47 | 10 | 56
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | To Date
Defects/Hour - Design Review | 1.88 | 13.3 | 4.5
Defects/Hour - Code Review | 8.07 | 4 | 7.59
Defects/Hour - Compile | 0 | #DIV/0! | 0
Defects/Hour - Test | 3.54 | 3.95 | 3.71
DRL (DLDR/UT) | 0.53 | 3.38 | 1.21
DRL (Code Review/UT) | 2.28 | 1.01 | 2.05
DRL (Compile/UT) | 0 | #DIV/0! | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 03:07 PM on 3/05/2017