## excel (3)
Project/Task | Phase | Start Time | Delta | Interrupt | Comment
/Non Project/PSP Fundamentals & Advanced/Program 7 | Planning | may 02, 2017 11:14:51 AM | 90 | 16
/Non Project/PSP Fundamentals & Advanced/Program 7 | Planning | may 02, 2017 01:13:11 PM | 35 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Planning | may 02, 2017 02:49:43 PM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Design | may 02, 2017 02:49:46 PM | 51 | 1
/Non Project/PSP Fundamentals & Advanced/Program 7 | Design | may 03, 2017 06:03:58 AM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Design Review | may 03, 2017 06:04:41 AM | 9 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 06:14:03 AM | 31 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 06:58:56 AM | 36 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 08:16:39 AM | 7 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 08:31:19 AM | 5 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 10:29:32 AM | 24 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code | may 03, 2017 11:15:40 AM | 25 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Code Review | may 03, 2017 11:40:24 AM | 15 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Test | may 03, 2017 11:55:08 AM | 56 | 2
/Non Project/PSP Fundamentals & Advanced/Program 7 | Test | may 03, 2017 01:23:50 PM | 20 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Postmortem | may 03, 2017 01:43:28 PM | 19 | 0
/Non Project/PSP Fundamentals & Advanced/Program 7 | Postmortem | may 03, 2017 02:37:42 PM | 27 | 0